## Read_Me
Event Budget & Expense Analysis
Project Overview
This independent portfolio project uses fictional event expense data to demonstrate spreadsheet reporting and budget analysis skills in Google Sheets.
Business Question
How does actual event spending compare with planned budgets, and which expense categories or events need attention?
Skills Demonstrated
Spreadsheet formulas and calculations
IF and COUNTIF functions
Pivot tables and data summarization
Charts and dashboard design
Conditional formatting
Budget variance analysis
Key Findings
Total planned budget: $29,500
Total actual spending: $29,900
Overall spending exceeded budget by $400.
Seven individual expense lines exceeded their budgets.
Recommendation
Review the over-budget expense lines to identify the causes of overspending. Use the event and category summaries to prioritize follow-up with vendors and improve future estimates.
All data in this project is fictional and created for portfolio practice.

## Event_Data
Event_ID | Event_Name | Category | Vendor | Budget | Actual_Cost | Variance | Budget_Status
EVT001 | Product Launch | Catering | Sample Catering Co | 2000 | 2350 | 350 | Over Budget
EVT001 | Product Launch | Venue | Sample Venue Co | 3000 | 2800 | -200 | Under Budget
EVT001 | Product Launch | Decor | Sample Decor Co | 800 | 950 | 150 | Over Budget
EVT002 | Team Celebration | Catering | Sample Catering Co | 1500 | 1400 | -100 | Under Budget
EVT002 | Team Celebration | Venue | Sample Venue Co | 1800 | 1900 | 100 | Over Budget
EVT002 | Team Celebration | Decor | Sample Decor Co | 500 | 450 | -50 | Under Budget
EVT003 | Client Reception | Catering | Sample Catering Co | 2500 | 2700 | 200 | Over Budget
EVT003 | Client Reception | Venue | Sample Venue Co | 3500 | 3500 | 0 | On Budget
EVT003 | Client Reception | Decor | Sample Decor Co | 1000 | 850 | -150 | Under Budget
EVT004 | Annual Meeting | Catering | Sample Catering Co | 3000 | 2800 | -200 | Under Budget
EVT004 | Annual Meeting | Venue | Sample Venue Co | 4000 | 4300 | 300 | Over Budget
EVT004 | Annual Meeting | Decor | Sample Decor Co | 1200 | 1100 | -100 | Under Budget
EVT005 | Networking Event | Catering | Sample Catering Co | 1800 | 1950 | 150 | Over Budget
EVT005 | Networking Event | Venue | Sample Venue Co | 2200 | 2100 | -100 | Under Budget
EVT005 | Networking Event | Decor | Sample Decor Co | 700 | 750 | 50 | Over Budget

## Dashboard
Event Budget Dashboard
Total Budget | 29500
Total Actual Spend | 29900
Total Variance | 400
Expense Lines Over Budget | 7
Budget Used % | 101.4%